## WORK LOG FOR CSC 106 ASS4
WORKLOG FOR CSC 106 ASSIGNMENT 4 (WESLEY CHOW)
DATE | TIME | DURATION (min) | PART # | GOAL | COMMENTS
2012-11-25 | 12:30pm | 45 | Whole project | Understanding the assignment and going through possible game candidates | Decided to choose QuidditchMatch-1 for analysis
2012-11-25 | 1:20pm | 60 | 1.1 | Finding positive features about the game | Uncertain whether features were actually positive or not; do this later
2012-11-25 | 2:06pm | 27 | 1.2 | Discussing a negative feature from the game | Starting positions of objects in the game are not defined explicitly.
2012-11-25 | 2:35pm | 20 | 1.3 | Creating a work plan | Three tasks
2012-11-25 | 3:05pm | 5 | 2.1 | Order 3 of Work Plan | Finished by Wesley
2012-11-25 | 3:05pm | 60 | 2.1 | Order 2 of Work Plan | Finished by Sebastian
2012-11-25 | 3:05pm | 69 | 2.1 | Order 1 of Work Plan | Unfinished, work on it later
2012-12-01 | 10:30am | 10 | 2.1 | Order 1 of Work Plan | Finished
2012-12-01 | 10:45am | 60 | All of Task 2 | Put everything together for Task 2, including pictures of the implementations | Did some photo editing,wrote reasons for difficulty ratings

## WORK PLAN FOR IMPLEMENTATION
WORK PLAN
ORDER | TASK | Time Estimate | Time Actual | Responsibility | Status
1 | Modify the position of the goalkeeper so he returns to the middle of the goalpost after each goal is scored on him | 5 minutes | 80 minutes | Wesley | Done
2 | Modify the quaffle's position to the center ring of the field after each goal | 10 minutes | 60 minutes | Sebastian | Done
3 | Ensure that the position of the quaffle starts at the center ring of the field when the game starts | 5 minutes | 5 minutes | Wesley | Done

## Sheet1
Task 1